Побудова логічної матриці спрямована на узагальнення та взаємозв’язок всіх складових проекту.

Матриця побудована для реалізації проекту для створення нової магістерської програми.

LOGICAL FRAMEWORK MATRIX

| Wider Objective: What is the overall broader objective, to which the project will contribute? What is the overall broader objective, to which the project will contribute? • To ensure that partner universities are in position to provide national economies of Macedonia (MK) and Ukraine (UA) with highly skilled specialists in Land governance trained in line with demand of modern practice and in accordance with Bologna process | Indicators of progress: What are the key indicators related to the wider objective? • Increasing interest among students to apply for the new Master programme in Land governance • Needs of stakeholders in new specialists are satisfied • All graduates are employed | How indicators will be measured: What are the sources of information on these indicators? • Number of the students who have chosen to study new Master programme • Feedback from main stakeholders • A number of graduates employed after after graduation |  |
| --- | --- | --- | --- |
| Specific Project Objective/s: What are the specific objectives, which the project shall achieve? - Specific Project Objective/s: What are the specific objectives, which the project shall achieve? - To develop and introduce a new Master programme in Land governance in accordance with Bologna process at partner universities by September 2012 - To establish new IT academic environment at partner Universities by September 2011 - To built up the capacity of SCMU, GDU and KNUCA, DNTU, KNAU, LNAU through intensive training by September 2012 - To strengthen the link between education and practice in Land governance - To enhance the visibility of the new Master programme in MK and UA by December 2012 | Indicators of progress: What are the quantitative and qualitative indicators showing whether and to what extent the project’s specific objectives are achieved? • New Master curriculum and courses are introduced together with teaching materials • The teachers are trained • Centres of Land governance are established • New IT academic environment is provided • Meeting between universities and the main stakeholders are arranged • The new Master programme is advertised outside the universities | How indicators will be measured: What are the sources of information that exist and can be collected? What are the methods required to get this information? • Monitoring of syllabus for each course • Monitoring of students' knowledge through different types of exam • Published new and/or updated teaching materials • Interviews and questionnaire for trained teachers, students and practitioners • Survey of use the Centre's facilities by teachers and students | Assumptions & risks: What are the factors and conditions not under the direct control of the project, which are necessary to achieve these objectives? What risks have to be considered? • Macedonian and Ukrainian governments might change priorities in the national land policy • University administrations fully support the project • The Ministry of Education and Science of Ukraine delays official accreditation of the programme • Trained teachers might leave the Universities • Purchase of equipment might be delayed due to VAT exemption procedure |

| Outputs (tangible) and Outcomes (intangible): Please provide the list of concrete outputs/outcomes leading to the specific objective/s, using bullet points, considering the following questions for their definition: What are the envisaged quantifiable and nonquantifiable effects and benefits of the project? What improvements and changes will be produced by the project? 1. Developed new Master curricula, courses and teaching materials 2. Newly established IT academic environment 3. Built up capacity of SCMU, GDU and KNUCA, DNTU, KNAU, LNAU 4. Strenghtened link between education and practice in Land governance 5. Enchanced visibility of the project and sustainability 6. Quality control and monitoring 7. Management of the project | Indicators of progress: What are the indicators to measure whether and to what extent the project achieves the envisaged results and effects? • Developed curricula cope with needs of stakeholders • Curricula are approved by the Universities Councils and accreditated by the Ministries of Education • Teaching materials are prepared and published • Centres of Land governance are in operation • Retrained teachers are capable of running the new MSc programme • Students' practical training and theses writing on state and private professional bodies is performed • Dissemination conferences are held • Websites are functioning • Informational booklets are published • Inter-project coaching is carried out • Local and international meetings of project management teams are held | How indicators will be measured: What are the sources of information on these indicators? • Approval of Universities Councils and Ministries of Education • Survey of available literature for each new course • Interviews with trained teachers and students • Course feedbacks • The website addresses • Survey of number of visitors of the websites • Survey of number of participants of dissemination conference • Reports on quality contol • Report on inter-project coaching • Monitoring report • Minutes of the kick-off and coordination meetings • Progress report • Final report | Assumptions & risks: What external factors and conditions must be realised to obtain the expected outcomes and results on schedule? • The Ministry of Education might postpone accreditation of new MSc programme • Centres of Land governance might attract a small number of visitors • Websites might be not available due to problems of Internet connection • Trained teachers might not have incentives to stay at the Universities • Professional bodies (private and public) may not have interest to cooperate with universities • Bachelor students may lack interests for new Master programme |
| --- | --- | --- | --- |
| Activities: What are the key activities to be carried out and in what sequence in order to produce the expected results? 1. Development of new MSc programme 2. Establishment of new IT academic environment 3.Building up of capacity of partner universities 4. Strengthening of link between education and practice 5.Dissemination and sustainability 6. Quality control and monitoring 7. Management of the project | Inputs: What inputs are required to implement these activities, e.g. staff time, equipment, mobilities, publications etc.? 1. Staff costs: 136255€, Cost of Stay and Travel costs: 25700€, Printing and Publishing costs: 20000€ 2. Staff costs: 4180€, Cost of Stay and Travel costs: 19700€, Equipment costs: 228300€ 3. Staff costs: 67000€, Cost of Stay and Travel costs: 106200€ 4. Staff costs: 6680€, Cost of Stay and Travel costs: 41906€ 5. Staff costs: 13100€, Cost of Stay and Travel costs: 47310€, Printing and Publishing costs: 15200€, Other costs: 14500€ 6. Staff costs: 24600€, Cost of Stay and Travel costs: 2436€, Other costs: 2500€ 7. Staff costs: 98250€, Cost of Stay and Travel costs: 56884€, Other costs 3000€, Overheads 65000€. |  | Assumptions, risks and pre-conditions: What pre-conditions are required before the project starts? What conditions outside the project’s direct control have to be present for the implementation of the planned activities? • The university administrations provide the Centres with premises and other facilities • Teaching staff is interested in learning and applying • Non-academic consortium members participate in the Reference team • Participants of mobility have reasonable skills in English |

Рабочий план

|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities | хх |  |  |  |  |  |  |  |  |  |  |  |